## Tabelle1
Redmine ID | Name | Schätzung |  |  | Additional Info | Status | Comments - Eliade - 14/7/2019 | Priority | Comments - Dush
Vorbereitung
14305 | Basic Functional Test for BAT |  | 5 | XXXL | Infrastruktur, Code Cleaning, Organisation | Done | Done
| JAR Export for Stand-Alone Excecution |  |  | M | New Task from 2018/10/12 | Done | Done
Testcases
14346 | Admin: Create new Vehicle |  | 1.5 | M |  | Done | Done same as 14408 | Prio 1 | duplicate and not required -New Test case #32062 created for vehicle creation(with HHT file) as Self Admin -New Test case #32063 created for vehicle creation(without HHT file) as Self Admin
14352 | Admin: Create new Vehicle (PSI / Fahrenheit) |  | 1 | S |  | Done | Done same as 14411 | Prio 1
14354 | User: Test Alert Notifications (Trailer) |  | 1.5 | L |  | Done | same as 14412 | Prio 1
14356 | Workshop view user |  | 1 | S |  | In Progress | user: test_ws_view sees yard reader 9884e399e109 but no vehicle is shown | Prio 3
14359 | Test Preparation |  | 2 | XL |  | Done | Done | Peio 1
14361 | Observation List – Update of new observations |  | 2 | XL |  | Open |  |  | is this to update sensor information via HHT file upload ?
14369 | KPIs: noAdmin, myFleet |  | 1.5 | L |  | Done | Done | Prio 2
14373 | KPIs: Admin, myFleet |  | 1.5 | L |  | Done | Done | Prio 2 | its duplicate with 14369 New Test case #32064 created to check the KPIs on Alerts page
14384 | Observation List – Update of changed observations |  | 2.25 | XL |  | Open |  | Prio 1 | is this test case to trigger alerts ? Then nothing is mentioned about sensor simulator
14385 | Sensor data available - normal user |  | 1.75 | XL |  | Done | Done | Prio 1
14386 | Observation List – Update of deleted observations |  | 2 | XL |  | Open |  | Prio 1
14408 | Admin: Create new Vehicle |  | 1.25 | M |  | Done | Done same as 14346 | Prio 1
14409 | Admin: Yard Reader assignment |  | 1 | S | Additional: "Old" depot has to assigned again to ensure testcase can be run multipel times with the same setting. | Done | Done | Prio 1
14410 | User: Test Alert Notifications |  | 1.25 | M | Can be skipped if it is to hard to implement | Done | Done | Prio 1 | duplicate with 14354
14411 | Admin: Create new Vehicle (PSI / Fahrenheit) |  | 1 | S |  | Done | Done same as 14352 | Prio 1
14412 | User: Test Alert Notifications (PSI / Fahrenheit) |  | 1 | S |  | Done | Done same as 14354¦for Conti Connect | Prio 1
14422 | Show / No-Show vehicle in Portal - Admin Check |  | 1.5 | L |  | Done | Done | Prio 1
14423 | Show / No-Show vehicle in Portal - NoAdmin Check |  | 1 | S |  | Done | Done | Prio 1
14538 | Fleet Hierarchy authorization |  | 1.5 | L |  | Open |  | Prio 2
14542 | MyFleet update |  | 1.25 | M |  | Done | Done | Prio 2
14549 | Check "Historic Report" in detailed view |  | 2.5 | XL | Chart Handling SVG Paring impementieren. Aufwand++ | Open |  | Prio 2
14572 | Historic Report - bar check |  | 1.5 | L | Chart Handling SVG Paring + | Done | Done | Prio 2
14573 | Historic Report - psi check |  | 1.25 | M | Chart Handling SVG Parsing | Done | Done | Prio 2
14578 | HHT upload |  | 1 | S | 2018/10/12: We need more than the descriped scenario. It has to be improved by adding more scenarios (HHT Files): more axles, different vehicles, and so on. | Done | Done | Prio 1
14584 | Delete recipien with no assignments |  | 1 | S |  | Done | Done | Prio 2
14586 | Delete recipien with assignments |  | 1 | S |  | Done | Done | Prio 2
32275 | FileDownloadAndContentTest |  |  | XL |  | Done | Done
14604 | Create recipien as fleet user & delete it with depot user |  | 1.5 | L |  | Done | Done | Prio 2 | Ojective not clear and description is confusing
x | Installation of Windows Client |  |  | L | Scheduled for Friday 23/1/2018 | Open
x | JAR Execution Documentation in RedMine |  |  | S |  | Done | Done

## Bugs
UserTestAlertNotificationsPsiFahrenheit | one user for normal page(tc+A) and for contiConnect
WorkshopViewUser_14356 | no vehicle attached to yardreader¦Andreas Vogel
Check "Historic Report" in detailed view | ocular needed
Fleet Hierarchy authorization | ????? 3288200
Observation List – Update of new observations Observation List – Update of changed observations Observation List – Update of deleted observations | explanation needed
How to make fleet depot, how to attach car to it TC_User_A and TC_User_B4 sees same car
user for creating customer user for creating workshopuser